## Microsoft CRM Project Plan
Project Plan
ID | Task Name | Resource Name | Task Status | Percent Complete | Budget Hours | Actual Hours | Remaining Hours | Start Date | End Date
1 | Project Totals |  |  | #DIV/0! | 0 | 0 | 0
2 | Envisioning+B38 Phase
3 | Initial Project Discovery
4 | Conduct Kickoff Meeting - Identify Critical Success Factors |  |  | #DIV/0! | 0 | 0 | 0
5 | Identify Technical requirements and Architecture
6 | Define Current Hardware Configuration (server and client) |  |  | #DIV/0! | 0 | 0 | 0
7 | Define Current Network Configuration |  |  | #DIV/0! | 0 | 0 | 0
8 | Define Current Software Configuration (that is, Microsoft SQL Server) |  |  | #DIV/0! | 0 | 0 | 0
9 | Review Microsoft CRM Hardware, Software, and Network Requirements |  |  | #DIV/0! | 0 | 0 | 0
10 | Identify Functional Requirements
11 | Prepare for Functional Requirements Session |  |  | #DIV/0! | 0 | 0 | 0
12 | Review and Document Business Process |  |  | #DIV/0! | 0 | 0 | 0
13 | Conduct Source System Review |  |  | #DIV/0! | 0 | 0 | 0
14 | Develop Functional Requirements |  |  | #DIV/0! | 0 | 0 | 0
15 | Develop Source Data Requirements |  |  | #DIV/0! | 0 | 0 | 0
16 | Conduct Gap Analysis (Existing CRM / Microsoft CRM) |  |  | #DIV/0! | 0 | 0 | 0
17 | Develop Interface/Import Requirements |  |  | #DIV/0! | 0 | 0 | 0
18 | Review and Identify Integration Requirements |  |  | #DIV/0! | 0 | 0 | 0
19 | Identify Acceptance Criteria
20 | Identify Key User Roles and Decision Makers |  |  | #DIV/0! | 0 | 0 | 0
21 | Identify/Document Key Functional Areas for Phase I |  |  | #DIV/0! | 0 | 0 | 0
22 | Identify Support Requirements |  |  | #DIV/0! | 0 | 0 | 0
23 | Integrate and Approve Requirements
24 | Review Requirements and Reconcile Conflicts |  |  | #DIV/0! | 0 | 0 | 0
25 | Develop Project Plan |  |  | #DIV/0! | 0 | 0 | 0
26 | Revise Risk Assessment |  |  | #DIV/0! | 0 | 0 | 0
27 | Revise Communications Strategy |  |  | #DIV/0! | 0 | 0 | 0
28 | Develop Gap Analysis/Features Map |  |  | #DIV/0! | 0 | 0 | 0
29 | Develop Statement of Work for Remaining Phases |  |  | #DIV/0! | 0 | 0 | 0
30 | Obtain Sign-Off on Integrated Requirements |  |  | #DIV/0! | 0 | 0 | 0
31 | Planning Phase
32 | Project Start-Up Processes
33 | Set Up Service Project |  |  | #DIV/0! | 0 | 0 | 0
34 | Initialize Project Plan |  |  | #DIV/0! | 0 | 0 | 0
35 | Identify Steering Committee |  |  | #DIV/0! | 0 | 0 | 0
36 | Identify Customer Project Management and Team Members |  |  | #DIV/0! | 0 | 0 | 0
37 | Identify Partner Team: Sales, Project Team Members |  |  | #DIV/0! | 0 | 0 | 0
38 | Develop Client Communication Plan |  |  | #DIV/0! | 0 | 0 | 0
39 | Project Control/Reporting Processes
40 | Establish Change Control Process |  |  | #DIV/0! | 0 | 0 | 0
41 | Establish Issue Management Process |  |  | #DIV/0! | 0 | 0 | 0
42 | Establish Status Tracking and Reporting Process |  |  | #DIV/0! | 0 | 0 | 0
43 | Project Initiation Process
44 | Develop Engagement Letter
45 | Document Business Strategy |  |  | #DIV/0! | 0 | 0 | 0
46 | Review Business Drivers |  |  | #DIV/0! | 0 | 0 | 0
47 | Review and Refine Project Objectives |  |  | #DIV/0! | 0 | 0 | 0
48 | Identify ROI Measurements to Be Used |  |  | #DIV/0! | 0 | 0 | 0
49 | Create and Submit Engagement Letter for Review |  |  | #DIV/0! | 0 | 0 | 0
50 | Obtain Signed Engagement Letter from Client |  |  | #DIV/0! | 0 | 0 | 0
51 | Prepare for Kickoff Meeting (agenda) |  |  | #DIV/0! | 0 | 0 | 0
52 | Development Phase
53 | Install All Required Software and Test |  |  | #DIV/0! | 0 | 0 | 0
54 | Design Process
55 | Design End-User, Administrator and UIM Training
56 | Develop Plans and Outlines: Audience, Approach |  |  | #DIV/0! | 0 | 0 | 0
57 | Design Testing Plan
58 | Develop Plan and Test Cases |  |  | #DIV/0! | 0 | 0 | 0
59 | Application User Interface Design
60 | Contacts |  |  | #DIV/0! | 0 | 0 | 0
61 | Accounts |  |  | #DIV/0! | 0 | 0 | 0
62 | Activities |  |  | #DIV/0! | 0 | 0 | 0
63 | Leads |  |  | #DIV/0! | 0 | 0 | 0
64 | Opportunities |  |  | #DIV/0! | 0 | 0 | 0
65 | Products |  |  | #DIV/0! | 0 | 0 | 0
66 | Quotes |  |  | #DIV/0! | 0 | 0 | 0
67 | Orders |  |  | #DIV/0! | 0 | 0 | 0
68 | Invoices |  |  | #DIV/0! | 0 | 0 | 0
69 | Cases |  |  | #DIV/0! | 0 | 0 | 0
70 | Contracts |  |  | #DIV/0! | 0 | 0 | 0
71 | Knowledge Base |  |  | #DIV/0! | 0 | 0 | 0
72 | Application Data Administration
73 | Define Organization and Business Units |  |  | #DIV/0! | 0 | 0 | 0
74 | Define Users and Teams |  |  | #DIV/0! | 0 | 0 | 0
75 | Define and Create Roles |  |  | #DIV/0! | 0 | 0 | 0
76 | Define Remote Users |  |  | #DIV/0! | 0 | 0 | 0
77 | Define Marketing Administration Data |  |  | #DIV/0! | 0 | 0 | 0
78 | Define Application Administration Data |  |  | #DIV/0! | 0 | 0 | 0
79 | Source Data Conversion Design
80 | Map Data |  |  | #DIV/0! | 0 | 0 | 0
81 | Create Data Conversion plan |  |  | #DIV/0! | 0 | 0 | 0
82 | Define Data Cleansing Plan |  |  | #DIV/0! | 0 | 0 | 0
83 | Design Initial Data Load |  |  | #DIV/0! | 0 | 0 | 0
84 | Review Mappings with Customer |  |  | #DIV/0! | 0 | 0 | 0
85 | Review Source Data Conversion Design |  |  | #DIV/0! | 0 | 0 | 0
86 | Recurring Interfaces
87 | Design Interface #1 |  |  | #DIV/0! | 0 | 0 | 0
88 | Design Interface #2 |  |  | #DIV/0! | 0 | 0 | 0
89 | Workflow Design
90 | Design Workflow Rules |  |  | #DIV/0! | 0 | 0 | 0
91 | Integration
92 | Requirements Review and Conversion Design |  |  | #DIV/0! | 0 | 0 | 0
93 | Integration Customization
94 | Design Mapping for New Touch Points |  |  | #DIV/0! | 0 | 0 | 0
95 | Configuration Process
96 | Application User Interface Creation
97 | Contacts |  |  | #DIV/0! | 0 | 0 | 0
98 | Accounts |  |  | #DIV/0! | 0 | 0 | 0
99 | Activities |  |  | #DIV/0! | 0 | 0 | 0
100 | Leads |  |  | #DIV/0! | 0 | 0 | 0
101 | Opportunities |  |  | #DIV/0! | 0 | 0 | 0
102 | Products |  |  | #DIV/0! | 0 | 0 | 0
103 | Quotes |  |  | #DIV/0! | 0 | 0 | 0
104 | Orders |  |  | #DIV/0! | 0 | 0 | 0
105 | Invoices |  |  | #DIV/0! | 0 | 0 | 0
106 | Cases |  |  | #DIV/0! | 0 | 0 | 0
107 | Contracts |  |  | #DIV/0! | 0 | 0 | 0
108 | Knowledge Base |  |  | #DIV/0! | 0 | 0 | 0
109 | Application Data Administration
110 | Create Organization and Business Units |  |  | #DIV/0! | 0 | 0 | 0
111 | Create Users and Teams |  |  | #DIV/0! | 0 | 0 | 0
112 | Create and Test Remote Users |  |  | #DIV/0! | 0 | 0 | 0
113 | Create Marketing Administration Data |  |  | #DIV/0! | 0 | 0 | 0
114 | Create Application Administration Data |  |  | #DIV/0! | 0 | 0 | 0
115 | Source Data Conversion
116 | Review Data Conversion Design Document |  |  | #DIV/0! | 0 | 0 | 0
117 | Create Source to Microsoft CRM Interfaces |  |  | #DIV/0! | 0 | 0 | 0
118 | Test Load of Source Data |  |  | #DIV/0! | 0 | 0 | 0
119 | Document Data Import Processes |  |  | #DIV/0! | 0 | 0 | 0
120 | Review Conversion Results |  |  | #DIV/0! | 0 | 0 | 0
121 | Recurring Interfaces
122 | Create Interface #1 |  |  | #DIV/0! | 0 | 0 | 0
123 | Create Interface #2 |  |  | #DIV/0! | 0 | 0 | 0
124 | Workflow Rules Creation
125 | Create and Test Workflow Rules |  |  | #DIV/0! | 0 | 0 | 0
126 | Integration
127 | Installation and Verification |  |  | #DIV/0! | 0 | 0 | 0
128 | Conversion and Verification |  |  | #DIV/0! | 0 | 0 | 0
129 | Integration Customization
130 | Create New Touch Points for Integration |  |  | #DIV/0! | 0 | 0 | 0
131 | Test the Data Movement |  |  | #DIV/0! | 0 | 0 | 0
132 | Validation Process
133 | User Review Sessions
134 | Configure/Unit Test Screens for Review Session 1 |  |  | #DIV/0! | 0 | 0 | 0
135 | Conduct URS 1 |  |  | #DIV/0! | 0 | 0 | 0
136 | Obtain and Document User Feedback |  |  | #DIV/0! | 0 | 0 | 0
137 | Refine Application - Unit Test for Final URS |  |  | #DIV/0! | 0 | 0 | 0
138 | Conduct Final URS |  |  | #DIV/0! | 0 | 0 | 0
139 | Obtain Sign-Off on Screen Configurations |  |  | #DIV/0! | 0 | 0 | 0
140 | System and Integration Test Execution
141 | Conduct System, Interface, Component Tests |  |  | #DIV/0! | 0 | 0 | 0
142 | Review Testing Results |  |  | #DIV/0! | 0 | 0 | 0
143 | Test Support Operations |  |  | #DIV/0! | 0 | 0 | 0
144 | Perform Final Validation Review, Sign Off |  |  | #DIV/0! | 0 | 0 | 0
145 | Project Quality Review
146 | Conduct Project Quality Review |  |  | #DIV/0! | 0 | 0 | 0
147 | Deployment Phase
148 | Develop Deployment Plans |  |  | #DIV/0! | 0 | 0 | 0
149 | Deliver End-User, Administrator, and IT Training |  |  | #DIV/0! | 0 | 0 | 0
150 | Load Source Data |  |  | #DIV/0! | 0 | 0 | 0
151 | Review Cut-Over and System Usage |  |  | #DIV/0! | 0 | 0 | 0
152 | Cut Over to Live System |  |  | #DIV/0! | 0 | 0 | 0
153 | Cut Over to Live Support |  |  | #DIV/0! | 0 | 0 | 0
154 | Monitor Systems |  |  | #DIV/0! | 0 | 0 | 0
155 | User Support and Guidance |  |  | #DIV/0! | 0 | 0 | 0
156 | Review Cut-Over and System Usage |  |  | #DIV/0! | 0 | 0 | 0
157 | Obtain Implementation Sign-Off |  |  | #DIV/0! | 0 | 0 | 0
162 | Post-Deployment Phase
163 | Transition from Project Team to Support |  |  | #DIV/0! | 0 | 0 | 0
164 | Complete Project Closeout Checklist |  |  | #DIV/0! | 0 | 0 | 0
165 | Archive Project Files |  |  | #DIV/0! | 0 | 0 | 0
166 | Write Debriefing Report |  |  | #DIV/0! | 0 | 0 | 0
167 | Write Staff Appraisals |  |  | #DIV/0! | 0 | 0 | 0
168 | Perform Benefits Assessment |  |  | #DIV/0! | 0 | 0 | 0
169 | Write Opportunity Report |  |  | #DIV/0! | 0 | 0 | 0
170 | Ongoing Project Management
171 | Ongoing Consultant Administration: Status, Document |  |  | #DIV/0! | 0 | 0 | 0
172 | Write Status Reports |  |  | #DIV/0! | 0 | 0 | 0
173 | Manage Project Plan and Actuals |  |  | #DIV/0! | 0 | 0 | 0
174 | Manage Change Control |  |  | #DIV/0! | 0 | 0 | 0
175 | Review and Maintain Issue Log |  |  | #DIV/0! | 0 | 0 | 0
176 | Maintain Risk Log |  |  | #DIV/0! | 0 | 0 | 0
177 | Conduct Project Status Meetings |  |  | #DIV/0! | 0 | 0 | 0
178 | Conduct Client Briefings |  |  | #DIV/0! | 0 | 0 | 0
179 | Conduct User Communications |  |  | #DIV/0! | 0 | 0 | 0
180 | Perform Day-to-Day Meetings and Issue Management |  |  | #DIV/0! | 0 | 0 | 0
Note on B64: The Microsoft CRM record types listed are a sample. This list is not a comprehensive list of all the Microsoft CRM record types.
Note on B101: The Microsoft CRM record types listed are a sample. This list is not a comprehensive list of all the Microsoft CRM record types.