## Microsoft CRM Project Plan
Project Plan: Rapid
ID | Task Name | Resource Name | Task Status | Percent Complete | Budget Hours | Actual Hours | Remaining Hours | Start Date | End Date
1 | Project Totals |  |  | #DIV/0! | 0 | 0 | 0
2 | Envisioning Phase
3 | Initial Project Discovery
4 | Conduct Kickoff Meeting - Identify Critical Success Factors |  |  | #DIV/0! | 0 | 0 | 0
5 | Identify Technical Requirements and Architecture
6 | Define Current Hardware Configuration (server and client) |  |  | #DIV/0! | 0 | 0 | 0
7 | Define Current Network Configuration |  |  | #DIV/0! | 0 | 0 | 0
8 | Define Current Software Configuration |  |  | #DIV/0! | 0 | 0 | 0
9 | Review Microsoft CRM Hardware, Software, and Network Requirements |  |  | #DIV/0! | 0 | 0 | 0
10 | Identify Functional Requirements
11 | Prepare for Functional Requirements Session |  |  | #DIV/0! | 0 | 0 | 0
12 | Review and Document Business Process |  |  | #DIV/0! | 0 | 0 | 0
13 | Conduct Source System Review |  |  | #DIV/0! | 0 | 0 | 0
14 | Develop Functional Requirements |  |  | #DIV/0! | 0 | 0 | 0
15 | Develop Source Data Requirements |  |  | #DIV/0! | 0 | 0 | 0
16 | Conduct Gap Analysis (Existing CRM / Microsoft CRM) |  |  | #DIV/0! | 0 | 0 | 0
17 | Identify Acceptance Criteria
18 | Identify Key User Roles and Decision Makers |  |  | #DIV/0! | 0 | 0 | 0
19 | Identify/Document Key Functional Areas for Phase I |  |  | #DIV/0! | 0 | 0 | 0
20 | Identify Support Requirements |  |  | #DIV/0! | 0 | 0 | 0
21 | Integrate and Approve Requirements
22 | Review Requirements and Reconcile Conflicts |  |  | #DIV/0! | 0 | 0 | 0
23 | Develop Project Plan |  |  | #DIV/0! | 0 | 0 | 0
24 | Revise Risk Assessment |  |  | #DIV/0! | 0 | 0 | 0
25 | Revise Communications Strategy |  |  | #DIV/0! | 0 | 0 | 0
26 | Develop Gap Analysis/Features Map |  |  | #DIV/0! | 0 | 0 | 0
27 | Develop Statement of Work for Remaining Phases |  |  | #DIV/0! | 0 | 0 | 0
28 | Obtain Sign-Off on Integrated Requirements |  |  | #DIV/0! | 0 | 0 | 0
29 | Planning Phase
30 | Project Start-Up Processes
31 | Set Up Service Project |  |  | #DIV/0! | 0 | 0 | 0
32 | Initialize Project Plan |  |  | #DIV/0! | 0 | 0 | 0
33 | Identify Steering Committee |  |  | #DIV/0! | 0 | 0 | 0
34 | Identify Customer Project Management and Team Members |  |  | #DIV/0! | 0 | 0 | 0
35 | Identify Partner Team: Sales, Project Team Members |  |  | #DIV/0! | 0 | 0 | 0
36 | Develop Client Communication Plan |  |  | #DIV/0! | 0 | 0 | 0
37 | Project Control/Reporting Processes
38 | Establish Change Control Process |  |  | #DIV/0! | 0 | 0 | 0
39 | Establish Issue Management Process |  |  | #DIV/0! | 0 | 0 | 0
40 | Establish Status Tracking and Reporting Process |  |  | #DIV/0! | 0 | 0 | 0
41 | Project Initiation Process
42 | Develop Engagement Letter
43 | Document Business Strategy |  |  | #DIV/0! | 0 | 0 | 0
44 | Review Business Drivers |  |  | #DIV/0! | 0 | 0 | 0
45 | Review and Refine Project Objectives |  |  | #DIV/0! | 0 | 0 | 0
46 | Identify ROI Measurements to Be Used |  |  | #DIV/0! | 0 | 0 | 0
47 | Create and Submit Engagement Letter for Review |  |  | #DIV/0! | 0 | 0 | 0
48 | Obtain Signed Engagement Letter from Client |  |  | #DIV/0! | 0 | 0 | 0
49 | Prepare for Kickoff Meeting (agenda) |  |  | #DIV/0! | 0 | 0 | 0
50 | Development Phase
51 | Install All Required Software and Test |  |  | #DIV/0! | 0 | 0 | 0
52 | Design Process
53 | Design End-User, Administrator, and UIM Training
54 | Develop Plans and Outlines: Audience, Approach |  |  | #DIV/0! | 0 | 0 | 0
55 | Design Testing Plan
56 | Develop Plan and Test Cases |  |  | #DIV/0! | 0 | 0 | 0
57 | Application User Interface Design
58 | Contacts |  |  | #DIV/0! | 0 | 0 | 0
59 | Accounts |  |  | #DIV/0! | 0 | 0 | 0
60 | Activities |  |  | #DIV/0! | 0 | 0 | 0
61 | Leads |  |  | #DIV/0! | 0 | 0 | 0
62 | Opportunities |  |  | #DIV/0! | 0 | 0 | 0
63 | Products |  |  | #DIV/0! | 0 | 0 | 0
64 | Quotes |  |  | #DIV/0! | 0 | 0 | 0
65 | Orders |  |  | #DIV/0! | 0 | 0 | 0
66 | Invoices |  |  | #DIV/0! | 0 | 0 | 0
67 | Cases |  |  | #DIV/0! | 0 | 0 | 0
68 | Contracts |  |  | #DIV/0! | 0 | 0 | 0
69 | Knowledge Base |  |  | #DIV/0! | 0 | 0 | 0
70 | Application Data Administration
71 | Define Organization and Business Units |  |  | #DIV/0! | 0 | 0 | 0
72 | Define Users and Teams |  |  | #DIV/0! | 0 | 0 | 0
73 | Define and Create Roles |  |  | #DIV/0! | 0 | 0 | 0
74 | Define Remote Users |  |  | #DIV/0! | 0 | 0 | 0
75 | Define Marketing Administration Data |  |  | #DIV/0! | 0 | 0 | 0
76 | Define Application Administration Data |  |  | #DIV/0! | 0 | 0 | 0
77 | Manual Source Data Conversion Design
78 | Map Physical Data Model |  |  | #DIV/0! | 0 | 0 | 0
79 | Create Data Conversion Plan |  |  | #DIV/0! | 0 | 0 | 0
80 | Define Data Cleansing Plan |  |  | #DIV/0! | 0 | 0 | 0
81 | Design Initial Data Load |  |  | #DIV/0! | 0 | 0 | 0
82 | Review Mappings with Customer |  |  | #DIV/0! | 0 | 0 | 0
83 | Review Source Data Conversion Design |  |  | #DIV/0! | 0 | 0 | 0
84 | Configuration Process
85 | Application User Interface Creation
86 | Contacts |  |  | #DIV/0! | 0 | 0 | 0
87 | Accounts |  |  | #DIV/0! | 0 | 0 | 0
88 | Activities |  |  | #DIV/0! | 0 | 0 | 0
89 | Leads |  |  | #DIV/0! | 0 | 0 | 0
90 | Opportunities |  |  | #DIV/0! | 0 | 0 | 0
91 | Products |  |  | #DIV/0! | 0 | 0 | 0
92 | Quotes |  |  | #DIV/0! | 0 | 0 | 0
93 | Orders |  |  | #DIV/0! | 0 | 0 | 0
94 | Invoices |  |  | #DIV/0! | 0 | 0 | 0
95 | Cases |  |  | #DIV/0! | 0 | 0 | 0
96 | Contracts |  |  | #DIV/0! | 0 | 0 | 0
97 | Knowledge Base |  |  | #DIV/0! | 0 | 0 | 0
98 | Application Data Administration
99 | Create Organization and Business Units |  |  | #DIV/0! | 0 | 0 | 0
100 | Create Users and Teams |  |  | #DIV/0! | 0 | 0 | 0
101 | Create and Test Remote Users |  |  | #DIV/0! | 0 | 0 | 0
102 | Create Marketing Administration Data |  |  | #DIV/0! | 0 | 0 | 0
103 | Create Application Administration Data |  |  | #DIV/0! | 0 | 0 | 0
104 | Manual Source Data Conversion
105 | Review Data Conversion Design Document |  |  | #DIV/0! | 0 | 0 | 0
106 | Test Load of Source Data |  |  | #DIV/0! | 0 | 0 | 0
107 | Document Data Import Processes |  |  | #DIV/0! | 0 | 0 | 0
108 | Review Conversion Results |  |  | #DIV/0! | 0 | 0 | 0
109 | Validation Process
110 | User Review Sessions
111 | Configure/Unit Test Screens for Review Session 1 |  |  | #DIV/0! | 0 | 0 | 0
112 | Conduct URS 1 |  |  | #DIV/0! | 0 | 0 | 0
113 | Obtain and Document User Feedback |  |  | #DIV/0! | 0 | 0 | 0
114 | Refine Application - Unit Test for Final URS |  |  | #DIV/0! | 0 | 0 | 0
115 | Conduct Final URS |  |  | #DIV/0! | 0 | 0 | 0
116 | Obtain Sign-Off on Screen Configurations |  |  | #DIV/0! | 0 | 0 | 0
117 | System and Integration Test Execution
118 | Conduct System, Interface, and Component Tests |  |  | #DIV/0! | 0 | 0 | 0
119 | Review Testing Results |  |  | #DIV/0! | 0 | 0 | 0
120 | Test Support Operations |  |  | #DIV/0! | 0 | 0 | 0
121 | Final Validation Review, Sign Off |  |  | #DIV/0! | 0 | 0 | 0
122 | Project Quality Review
123 | Conduct Project Quality Review |  |  | #DIV/0! | 0 | 0 | 0
124 | Deployment Phase
125 | Develop Deployment Plans |  |  | #DIV/0! | 0 | 0 | 0
126 | Deliver End-User, Administrator, and IT Training |  |  | #DIV/0! | 0 | 0 | 0
127 | Load Source Data |  |  | #DIV/0! | 0 | 0 | 0
128 | Review Cut-Over and System Usage |  |  | #DIV/0! | 0 | 0 | 0
129 | Cut Over to Live System |  |  | #DIV/0! | 0 | 0 | 0
130 | Cut Over to Live Support |  |  | #DIV/0! | 0 | 0 | 0
131 | Monitor Systems |  |  | #DIV/0! | 0 | 0 | 0
132 | User Support and Guidance |  |  | #DIV/0! | 0 | 0 | 0
133 | Review Cut-Over and System Usage |  |  | #DIV/0! | 0 | 0 | 0
134 | Obtain Implementation Sign-Off |  |  | #DIV/0! | 0 | 0 | 0
140 | Post-Deployment Phase
141 | Transition from Project Team to Support |  |  | #DIV/0! | 0 | 0 | 0
142 | Complete Project Closeout Checklist |  |  | #DIV/0! | 0 | 0 | 0
143 | Archive Project Files |  |  | #DIV/0! | 0 | 0 | 0
144 | Write Debriefing Report |  |  | #DIV/0! | 0 | 0 | 0
145 | Write Staff Appraisals |  |  | #DIV/0! | 0 | 0 | 0
146 | Perform Benefits Assessment |  |  | #DIV/0! | 0 | 0 | 0
147 | Write Opportunity Report |  |  | #DIV/0! | 0 | 0 | 0
148 | Ongoing Project Management
149 | Ongoing Consultant Administration: Status, Document |  |  | #DIV/0! | 0 | 0 | 0
150 | Write Status Reports |  |  | #DIV/0! | 0 | 0 | 0
151 | Manage Project Plan and Actuals |  |  | #DIV/0! | 0 | 0 | 0
152 | Manage Change Control |  |  | #DIV/0! | 0 | 0 | 0
153 | Review and Maintain Issue Log |  |  | #DIV/0! | 0 | 0 | 0
154 | Maintain Risk Log |  |  | #DIV/0! | 0 | 0 | 0
155 | Conduct Project Status Meetings |  |  | #DIV/0! | 0 | 0 | 0
156 | Conduct Client Briefings |  |  | #DIV/0! | 0 | 0 | 0
157 | Conduct User Communications |  |  | #DIV/0! | 0 | 0 | 0
158 | Perform Day-to-Day Meetings and Issue Management |  |  | #DIV/0! | 0 | 0 | 0
Note on B62: The Microsoft CRM record types listed are a sample. This list is not a comprehensive list of all the Microsoft CRM record types.
Note on B90: The Microsoft CRM record types listed are a sample. This list is not a comprehensive list of all the Microsoft CRM record types.