## Phase 1 Project Time
Status Tracking: Project Time
| Task Name | Resource | Status | % Complete | Budget | Actual | Remaining | Week Ending
Organization Name]
1 | Software Installation
2 | Install all server software |  | In Process | 0 | 1 |  | 1
3 | Install client software for core group |  |  | 0 | 1 |  | 1
4 | Application User Interface Changes
5 | Accounts |  |  | 0 | 1 |  | 1
6 | Contacts |  |  | 0 | 1 |  | 1
7 | Activities |  |  | 0 | 1 |  | 1
8 | Leads |  |  | 0 | 1 |  | 1
9 | Opportunities |  |  | 0 | 1 |  | 1
10 | Products |  |  | 0 | 1 |  | 1
11 | Quotes |  |  | 0 | 1 |  | 1
12 | Orders |  |  | 0 | 1 |  | 1
13 | Invoices |  |  | 0 | 1 |  | 1
14 | Cases |  |  | 0 | 1 |  | 1
15 | Contracts |  |  | 0 | 1 |  | 1
16 | Knowledge Base |  |  | 0 | 1 |  | 1
17 | Application Data Administration
18 | Define and create organization and business units |  |  | 0 | 1 |  | 1
19 | Define and create users and teams |  |  | 0 | 1 |  | 1
20 | Define and create roles |  |  | 0 | 1 |  | 1
21 | Design of Other Integration
22 | Design, develop, and test other integration |  |  | 0 | 1 |  | 1
23 | Source Data Conversion
24 | Map source data to Microsoft CRM |  |  | 0 | 1 |  | 1
25 | Extract, clean, and load source data into Microsoft CRM |  |  | 0 | 1 |  | 1
26 | Review and sign-off |  |  | 0 | 1 |  | 1
27 | Report Changes
28 | Research reporting requirements |  |  | 0 | 1 |  | 1
29 | Create necessary queries or exports to outside database |  |  | 0 | 1 |  | 1
30 | Acceptance Testing
31 | Create Acceptance test scenarios |  |  | 0 | 1 |  | 1
32 | Conduct Acceptance test |  |  | 0 | 1 |  | 1
33 | Integration
34 | Install integration components |  |  | 0 | 1 |  | 1
35 | Data load and verification |  |  | 0 | 1 |  | 1
36 | Test functionality |  |  | 0 | 1 |  | 1
37 | Integration Customization
38 | Design requirements |  |  | 0 | 1 |  | 1
39 | Make design changes |  |  | 0 | 1 |  | 1
40 | Review and sign-off |  |  | 0 | 1 |  | 1
41 | Training and Documentation
42 | Create training documentation and process document |  |  | 0 | 1 |  | 1
43 | Deliver user training |  |  | 0 | 1 |  | 1
44 | Deliver administrator training to administrative users |  |  | 0 | 1 |  | 1
45 | Other
46 | Deployment and Initial Go-live Support
47 | Final data load and verification |  |  | 0 | 1 |  | 1
48 | Establish production environment |  |  | 0 | 1 |  | 1
49 | Go-live support |  |  | 0 | 1 |  | 1
50 | Project Administration
51 | Administration |  |  | 0 | 1 |  | 1
52 | Miscellaneous meetings |  |  | 0 | 1 |  | 1
53 | Ongoing Project Management
54 | Write status reports |  |  | 0 | 1 |  | 1
55 | Manage project plan and actuals |  |  | 0 | 1 |  | 1
56 | Manage change control |  |  | 0 | 1 |  | 1
57 | Review and maintain issue log |  |  | 0 | 1 |  | 1
58 | Conduct project status meetings |  |  | 0 | 1 |  | 1
59 | Perform day-to-day meetings and issue management |  |  | 0 | 1 |  | 1
| Total Phase 1 - Hours |  |  | 0 | 45 | 0 | 45
Note on B8: The Microsoft CRM record types listed are a sample. This list is not a comprehensive list of all the Microsoft CRM record types.

## Phase 1 Milestone Schedule
Status Tracking: Milestones
| Start | Complete | Status | Milestones | Consultant(s) on Site
Week 1:
Week 2:
Week 3:
Week 4:
Week 5:
Week 6:
Week 7:
Week 8:

## Issue Tracking
Status Tracking: Issues
Color Legend: | Closed This Week | Severity: | 1 - Critical | 2- High | 3- Medium | 4- Low
Critical Risk Issue
|  |  | Date |  |  |  | Date
Milestone | Issue No. | Problem/Issue | Opened | User | Owner | Status | Completed | Comments | Severity | Due Date